## Read Me
Zero Trust Transition Readiness Scorecard
Companion artifact to the Transition-State Zero Trust Adoption Toolkit, v0.1.
What this is for
A structured baseline of the capabilities that determine how safely an organization can migrate incrementally toward zero trust. Run it before a major migration wave, and again after material change.
Sheets
Scorecard The working sheet. Shaded cells are yours to complete.
Sample A fully worked example for a county IT organization.
Scoring scale What each score from 0 to 5 means.
How to use it
1. Score Current honestly. A low score is useful information, not a failure.
2. Set Target for where the domain needs to be before the next wave, not an end state.
3. Record the evidence you looked at. This is what makes the score defensible later.
4. Work the 0s and 1s first. They are where transition risk concentrates.
Notes
The Gap column calculates itself. Everything else is manual.
This is a planning aid, not a compliance determination or an audit result.
Sample values are constructed for illustration and are not from a real organization.

## Scorecard
Zero Trust Transition Readiness Scorecard
Score each domain 0-5 for today (Current) and for where it needs to be before the next migration wave (Target). Shaded cells are for you to complete.
Domain | Current | Target | Gap | Evidence reviewed | Observed gap | Priority | Action | Owner
Asset inventory | 2 | 4 | 2 | CMDB export 08-Mar; Lansweeper scan 11-Mar | Scan found 94 devices absent from the CMDB, mostly at the two annex sites. | High | Reconcile CMDB against discovery scan before wave 1 | D. Whitfield | <- example row; overwrite or delete
Identity readiness
Privileged access governance
Endpoint visibility
Network segmentation readiness
Logging and monitoring
Data sensitivity awareness
Backup and disaster recovery
Application dependency visibility
Documentation maturity
Internal team readiness
Exception governance
Summary
Domains scored | 1
Average current score | 2
Average target score | 4
Domains at 0 or 1 (address first) | 0
Domains already at target | 0
Scores are a planning aid, not an audit result. Record the evidence you relied on so a later reviewer can see what the score was based on.

## Sample
Sample: county government, baseline before wave 1
Illustrative values for a 1,200-staff county IT organization. Figures are constructed for demonstration and are not results from a real organization.
Domain | Current | Target | Gap | Evidence reviewed | Observed gap | Priority | Action | Owner
Asset inventory | 2 | 4 | 2 | CMDB export 08-Mar; Lansweeper scan 11-Mar | Scan found 94 devices absent from the CMDB, mostly at the two annex sites. | High | Reconcile CMDB against discovery scan before wave 1 | D. Whitfield
Identity readiness | 3 | 4 | 1 | Entra ID tenant review; app inventory | Eleven line-of-business apps still authenticate against the legacy directory. | High | Sequence SSO migration for the eleven apps | R. Okonkwo
Privileged access governance | 2 | 4 | 2 | Admin group export 05-Mar | Six standing domain admin accounts; no periodic review has been run. | Critical | Stand up quarterly access review; move to just-in-time elevation | R. Okonkwo
Endpoint visibility | 3 | 4 | 1 | EDR console coverage report | EDR covers laptops and desktops; not deployed to the 40 kiosk units. | Medium | Extend EDR to kiosks or place them in a restricted segment | T. Alvarado
Network segmentation readiness | 1 | 3 | 2 | Firewall ruleset export; no flow data | Flat internal network. East-west traffic is not mapped or restricted. | Critical | Complete flow discovery before any enforcement change | T. Alvarado
Logging and monitoring | 3 | 4 | 1 | SIEM source inventory 12-Mar | Cloud control-plane logs are not forwarded to the SIEM. | High | Onboard cloud audit logs ahead of cutover | S. Behrendt
Data sensitivity awareness | 2 | 3 | 1 | Records retention schedule (2019) | Classification policy exists but is not applied to the migrating workloads. | Medium | Tag in-scope workloads using the existing approved scheme | M. Iyer
Backup and disaster recovery | 2 | 4 | 2 | Veeam job report; no restore test on file | Backups run nightly. The last documented restore test was in 2023. | High | Perform and document a restore test for each wave-1 workload | S. Behrendt
Application dependency visibility | 1 | 4 | 3 | Interviews with app owners | Dependencies are held informally. The permits system has undocumented callers. | Critical | Map dependencies for wave-1 and wave-2 workloads | D. Whitfield
Documentation maturity | 1 | 3 | 2 | SharePoint architecture folder | Diagrams are two refresh cycles out of date; runbooks cover three systems only. | Medium | Refresh diagrams as each wave completes | M. Iyer
Internal team readiness | 2 | 4 | 2 | Team skills matrix 14-Mar | Two staff hold cloud certifications. Neither has run a production cutover. | High | Shadowing plan plus one supervised task per engineer | D. Whitfield
Exception governance | 0 | 4 | 4 | None located | No register exists. Temporary firewall rules are tracked in email threads. | Critical | Stand up the transition-state risk register in week 2 | R. Okonkwo
Summary
Domains scored | 12
Average current score | 1.8
Average target score | 3.8
Domains at 0 or 1 (address first) | 4
Critical priority actions | 4

## Scoring scale
Scoring scale
Score | Meaning
0 | Unknown or undocumented
1 | Informal / ad hoc
2 | Partially documented
3 | Controlled but not repeatable
4 | Repeatable and reviewed
5 | Automated, monitored, and continuously improved
A score of 3 means the control works but is not yet consistent run to run. Most organizations mid-migration sit between 1 and 3.