## Read Me
Transition-State Risk Register
Companion artifact to the Transition-State Zero Trust Adoption Toolkit, v0.1.
What this is for
Temporary exceptions are created during every migration. This register makes each one visible, owned, monitored and time-bound, so that it gets retired instead of quietly becoming permanent.
Sheets
Register The working sheet. Shaded cells are yours to complete.
Sample Six worked entries, including one that had to be extended.
The rule this register exists to enforce
An exception with no named owner, no monitoring method and no retirement condition is not a temporary measure. It is unmanaged risk. If you cannot fill those three fields, reconsider granting the exception at all.
Field notes
Reason for exception If this cannot be stated plainly, the exception is questionable.
Compensating control What reduces the risk while the exception is open.
Expiry / review A date, always. Not "end of project".
Retirement condition The specific event that allows closure, e.g. "workload X migrated".
Status Open, Extended, or Closed.
Notes
Summary counts calculate themselves, including rows missing an owner or a retirement condition.
Extending an exception needs a new date and a stated reason. Silent rollover defeats the purpose.
Sample values are constructed for illustration and are not from a real organization.

## Register
Transition-State Risk Register
One row per temporary condition created while legacy systems and zero trust controls coexist. A row without an owner, a monitoring method and a retirement condition is unmanaged risk.
Risk ID | System / workload | Temporary exception | Reason for exception | Compensating control | Monitoring method | Risk rating | Business owner | Technical owner | Security owner | Opened | Expiry / review | Retirement condition | Status | Evidence link
TSR-001 | Legacy HR portal | Local password authentication retained | Vendor SSO connector is not available until the 7.4 release | MFA enforced at VPN; daily review of portal logins | Weekly SIEM query, results filed in the migration folder | High | HR Director | R. Okonkwo | S. Behrendt | 2026-03-18 | 2026-10-31 | Local authentication disabled after SSO upgrade completes | Open | ops/TSR-001/ | <- example row; overwrite or delete
Summary
Exceptions recorded | 1
Open | 1
Extended | 0
Closed | 0
High rating and still open | 1
Missing a technical owner | 0
Missing a retirement condition | 0
Status values: Open, Extended, Closed. Use Extended only with a new dated reason, never as a silent rollover.

## Sample
Sample: county government, wave 1 and wave 2
Constructed for illustration; not results from a real organization. Note TSR-006, which could not be closed on time and was extended with a stated reason rather than left to lapse.
Risk ID | System / workload | Temporary exception | Reason for exception | Compensating control | Monitoring method | Risk rating | Business owner | Technical owner | Security owner | Opened | Expiry / review | Retirement condition | Status | Evidence link
TSR-001 | Legacy HR portal | Local password authentication retained | Vendor SSO connector is not available until the 7.4 release | MFA enforced at VPN; daily review of portal logins | Weekly SIEM query, results filed in the migration folder | High | HR Director | R. Okonkwo | S. Behrendt | 2026-03-18 | 2026-10-31 | Local authentication disabled after SSO upgrade completes | Open | ops/TSR-001/
TSR-002 | Payment reporting DB | Broad temporary subnet allow rule | Reporting callers not yet enumerated; dependency discovery incomplete | Source-IP restriction to the reporting subnet; database audit logging on | Daily rule-hit report; alert on any source outside the range | High | Finance Director | T. Alvarado | S. Behrendt | 2026-03-18 | 2026-09-30 | Broad rule replaced with per-caller rules after discovery | Open | ops/TSR-002/
TSR-003 | Backup management | Privileged local service account | Backup product does not yet support the PAM broker | Credential held in vault; seven-day rotation; use alerts to SOC | Rotation log reviewed at each 30/60/90 checkpoint | Medium | IT Operations Manager | S. Behrendt | S. Behrendt | 2026-03-25 | 2026-11-15 | Service account moved into PAM-managed workflow | Open | ops/TSR-003/
TSR-004 | Permits system | Direct database read from the new reporting service | Reporting service went live before the permits database migrated | Path restricted to one source address; alert on any second source | Weekly log review, notes filed with the register | Medium | Planning Director | D. Whitfield | S. Behrendt | 2026-04-02 | 2026-08-14 | Reporting service repointed to the migrated database | Closed | ops/TSR-004/closure.md
TSR-005 | Kiosk units (annex sites) | EDR agent not deployed | Kiosk image does not support the current agent build | Kiosks isolated in a restricted VLAN with no server-side access | Monthly VLAN membership check | Medium | IT Operations Manager | T. Alvarado | S. Behrendt | 2026-04-02 | 2026-12-19 | Kiosks reimaged with a supported build, or retired | Open | ops/TSR-005/
TSR-006 | File server (annex 2) | Windows Server 2012 R2 host retained | Replacement hardware is in the FY27 capital budget, not FY26 | Host isolated in its own segment; access logged and alerted | Quarterly review at the assurance checkpoint | High | IT Operations Manager | T. Alvarado | S. Behrendt | 2026-03-18 | 2027-03-31 | Host replaced and decommissioned under the FY27 refresh | Extended
Summary
Exceptions recorded | 6
Open | 4
Extended | 1
Closed | 1
High rating and still open | 2